## Sprint1
User Story | Story point | Assigned To | Status | Original Estimate(hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US 1.1 Login | 1 |  | completed | 2
|  | Dikshant chapapagain | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Backend Development (Database)
Frontend Development(Design) |  | Dristi Sapkota | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0.5
US. 1.2 Signup | 2 |  | completed | 1
Backend Development (Database) |  | Dikshant chapapagain | 1.5 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0.5
Frontend Development(Design) |  | Dristi Sapkota | 1.5 | 1 | 2 | 0 | 0 | 0 | 0 | 0.5
US 1.3 Forget pass | 3 |  | completed | 0.5
Backend Development (Database) |  | Dikshant chapapagain | 1.5 |  | 0 | 0 | 0 | 0 | 0 | 0.5
Frontend Development(Design) |  | Dristi Sapkota | 1.5 |  | 0.5 | 0 | 0 | 0 | 0 | 0
US 1.4 Google Signup | 2 |  | Completed
Backend Development (Database) |  | Dikshant chapapagain | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 2
Backend Development (Database) |  | Rohit | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 2
US 1.5 Ui/UX | 3 |  | Completed
Backend Development (Database) |  | Dikshant chapapagain | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 2
Backend Development (Database) |  | Rohit Shah | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 2

## Sprint2
User Story | Story Point | Assigned To | Status | Original Estimate(hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 |  | Sprint Review
Navigation Buttons (2.1) | 1 |  | Completed
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 1 | 0 | 0.5 | 0.5 | 0 |  | 0.5
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | 0
(2.1) Dashboard Page | 0.5 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 1 | 0.5 | 0 | 0.5 | 0 |  | 0.5
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0.5
(2.3) Maps Page | 2 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 1
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | 1
(2.4) User Profile Page | 2 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0
Frontend Development(Design) |  | Rohit Shah | 0 | 2 | 0 | 0.5 | 0.5 | 0.5 | 0 |  | 2
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Hero Section (2.6) | 3 |  | Completed | 0
Backend Development (Database) |  | Resha Adhikari | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0
Frontend Development(Design) |  | Sambridhi Chauhan | 0 | 2 | 0 | 1.5 | 0.5 | 1 | 0 |  | 2
Backend Development (Database) |  | Anshuya sayaju | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | 2

## Call log
Sprint 1 | Date | Time | Remarks
Day 1 | 2025-05-14 | (8:28-8:34)PM | Team Meetup and Talk
Day 2 | 2025-05-15 | (6:31-6:38)PM | Project Discussion
Day 3 | 2025-05-16 | (8:12-8:21)PM | UI/UX Design Discussion
Day 4 | 2025-05-18 | (7:55-8:04)PM | UI/UX Design Implementation
Day 5 | 2024-12-22 | (7:58-8:10)PM | Frontend Discussion
Sprint 2
Day 1 | 2025-05-23 | 10:00-10:06)PM | Frontend Implementation
Day 2 | 2025-05-25 | (10:06-10:13)PM | Frontend Implementation
Day 3 | 2025-05-26 | (10:13-10:22)PM | Backend Discussed
Day 4 | 2025-05-27 | (10:22-10:31)PM | Backend Implementation Discussed
Day 5 | 2025-05-28 | (10:31-10:43)PM | Bakcend

## Sprint3
User Story | Story Point | Assigned To | Status | Original Estimate(hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Sign Up Form (2.7)
Backend Development (Database) |  | Dikshanta Chapagin | Completed | 1 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota |  | 0.5 | 0 | 0.5 | 0.5 | 1 | 0.5
Backend Development (Database) |  | Rohit Shah |  | 1 | 0 | 0 | 0 | 0 | 0
Sign Up Button(2.8)
Backend Development (Database) |  | Dikshanta Chapagin | Completed | 0.5 | 0 | 0 | 1 | 0.5 | 1
Frontend Development(Design) |  | Dristi Sapkota |  | 1 | 0 | 0 | 0.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah |  | 1 | 0 | 0 | 0 | 0 | 0
Log in Form(2.9)
Backend Development (Database) |  | Dikshanta Chapagin | Completed | 0.5 | 0 | 0 |  | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota |  | 2 | 0.5 | 0 | 0.5 | 1 | 0
Backend Development (Database) |  | Rohit Shah |  | 1 | 0 | 0 | 0 | 0 | 0
Log in Button(3.0)
Backend Development (Database) |  | Dikshanta Chapagin | Completed | 0.5 | 0 | 0 | 0 | 0 | 1
Frontend Development(Design) |  | Dristi Sapkota |  | 1 | 0 | 0 | 0.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah |  | 2 | 0 | 0 | 0.5 | 1 | 0

## Sprint4
User Story | Story Point | Assigned To | Status | Original Estimate(hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Booking appointment Display (3.1) | 1 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Personal Details Input (3.2) | 0.5 |  | Ongoing | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0.5 | 0 | 0 | 1.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SymptomAnalyzer Input (3.3) | 2 |  | Ongoing | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 1 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 3 | 0 | 1 | 0.5 | 0 | 0 | 0
MapsActivity (3.4) | 2 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 3 | 0 | 0 | 1 | 0.5 | 1 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 3 | 0 | 0 | 0 | 0.5 | 0 | 0
Xray-Analysis (3.5) | 3 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 0.5 | 0 | 0 | 1 | 0 | 1 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
ChatbotActivity4.1 | 3 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0 | 1 | 0.5 | 0 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint5
User Story | Story Point | Assigned To | Status | Original Estimate(hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
DoctorBooking (4.1) | 1 |  | Ongoing | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 1 | 0 | 0 | 0 | 0.5 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
ChatbotActivity (4.2) | 0.5 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0 | 0.5 | 0 | 0.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
ProfilePage (4.3) | 2 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0 | 1 | 0.5 | 0 | 1 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0.5 | 0
UtiltiesSection(4.4) | 2 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0.5 | 0.5 | 1.5 | 0.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet7
User Story | Story Point | Assigned To | Status | Original Estimate(hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
BookAppointment (5.1) | 1 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
ChatbotVoice (5.2) | 0.5 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 2 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0
Hospitals/Pharmacy (5.4) | 2 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 2 | 0 | 0.5 | 0.5 | 0 | 0 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Xray-Analysis (5.5) | 2 |  | Completed | 0
Backend Development (Database) |  | Dikshanta Chapagin | 0 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0
Frontend Development(Design) |  | Dristi Sapkota | 0 | 1 | 0 | 0.5 | 1 | 0 | 0.5 | 0
Backend Development (Database) |  | Rohit Shah | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0